## Slide 1: Northeast Corridor Atlantic Coast Routes (NEC ACR) 11/5/2020 Implementation

## Slide 2: What We Are Doing, Why, When
What: 39 new/amended Q Routes and Y Routes will replace the north-south high-altitude route structure along the east coast of the United States
Why: Transition to a PBN-Centric NAS thus decreasing reliance on ground-based NAVAIDs
When: Changes being implemented on 13 separate chart dates 10/10/2019 through 1/27/2022
NEC ACR is one of the biggest changes to the National Airspace System (NAS) in decades

## Slide 3: BEFORE
Not all central and western U.S. Routes are depicted
Q-Routes depicted in green
Y-Routes depicted in gray
J-Routes depicted in blue

## Slide 4: FUTURE STATE 12/2/2021
Not all central and western U.S. Routes are depicted
Q-Routes depicted in green
Y-Routes depicted in gray
J-Routes depicted in blue

## Slide 5: 2020 Implementation Milestones
10/10/2019 Publish/Implement 1 New Y-Route and 8 Waypoints
11/7/2019 Implement ZDC Low Altitude Sector Changes
12/5/2019 NOTAM NA 33 J-Routes/Q-Routes (FL Metroplex) for 56 days
1/30/2020 Delete/Amend 33 J-Routes/Q-Route (FL Metroplex), Cancel N/A NOTAM
1/30/2020 Delete 5 CHS STARs
3/26/2020 Delete/Amend 6 SIDs (BWI/IAD/DCA/HEF/ADW)
5/21/2020 Amend 2 Q-Routes: Q75, Q475
5/21/2020 Amend 1 SID (DOV)
7/16/2020 Delete/Amend 18 J-Routes
9/10/2020 Publish/Amend 32 Q-Routes, 4 Y-Routes, NOTAM N/A for 56 days
9/10/2020 Amend 1 SID (ATL)
10/8/2020 Implement ZDC Ultra High Sector 30 and 3 minor airspace changes
11/5/2020 Implement 32 Q-Routes, 4 Y-Routes, Cancel N/A NOTAM
11/5/2020 Publish/Delete/Amend 14 STARs (PHL/EWR/TEB/LGA/DOV/WRI)
11/5/2020 Publish/Delete/Amend 29 SIDs/STARs/SIAPs (CHS/JZI/RDU)
11/5/2020 Delete/Amend 31 J-Routes, 1 Q-Route, Cancel N/A NOTAM
12/31/2020 Delete 2 STARs (LGA/EWR)
RE-PLANNED
DUE TO COVID-19

## Slide 6: NEC ACR Changes - 2020
9/10/2020 (8) Q-Route Additions/Amendments
  Publish New Q119, Q127, Q129, Q220, Q430, Q439, Q450 per original 18-AEA-16
  Amend Q480 per original 18-AEA-16
  IMPORTANT: All of the above routes EXCEPT Q480 will be NOTAM’d NA on 9/10/2020 for one chart cycle.
  EXCEPT FOR Q480, PLEASE DO NOT FILE THESE ROUTES UNTIL 11/5/2020.
11/5/2020 (11) J-Route/Q-Route Deletions/Amendments
  Delete J62, J109, J230, J570, Q108 per original 19-ASO-27
  Amend J2 (del TAY-DEFUN), J39 (del CEW-MGM), J61 (del EDDYS-EMI) per original 19-ASO-27
  Amend (with changes) J37 (del ALB-MSS), J55 (del CHS-TUBAS), J121 (del BRIGS-ENE)
11/5/2020 (18) SIDs/STARs/SIAPs
  Amend TEB MAZIE3 STAR
  Publish STARs: LGA (APPLE1), EWR (BRAND1), DOV (ARLFT1), WRI (WAALK1)
  Delete STARs: LGA (GATBY1), EWR (RUUTH1), DOV (SMYRNA3), WRI (SEA ISLE4)
  Amend CHS SIDs (PLMTO3, LGRHD3, JZI-KIAWAH2)
  Amend CHS STARs: (AMYLU3, OSPRI7)
  Amend CHS RNAV (GPS) Y APCHs (RWYS 03, 21, 15, 33)

## Slide 7: Q-Route NA NOTAMs Effective 9/10/2020-11/5/2020
!FDC 0/9537 ZDC, !FDC 0/9539 ZNY
  ROUTE ZDC ZNY. Q119 SCOOB, VA TO WESTMINSTER (EMI) VORTAC, MD NA.
!FDC 0/9540 ZDC
  ROUTE ZDC. Q127 GORDONSVILLE (GVE) VORTAC, VA TO SMYRNA (ENO) VORTAC, DE NA.
!FDC 0/9541 ZDC
  ROUTE ZDC. Q129 GARIC, NC TO PYTON, MD NA.
!FDC 0/9542 ZBW
  ROUTE ZBW. Q220 RIFLE, NY TO LARIE, MA NA.
FDC 0/9544 ZNY, !FDC 0/9543 ZBW, !FDC 0/9546 ZOB
  ROUTE ZNY ZBW ZOB. Q430 ZANDR, OH TO NANTUCKET (ACK) VOR/DME, MA NA.
!FDC 0/9684 ZDC, !FDC 0/9682 ZNY, !FDC 0/9681 ZBW
  ROUTE ZDC ZNY ZBW. Q439 BRIGS, NJ TO PRESQUE ISLE (PQI) VOR/DME, ME NA.
!FDC 0/9549 ZNY
  ROUTE ZNY. Q450 HNNAH, NJ TO DEER PARK (DPK) VOR/DME, NY NA.

## Slide 8: How Operators Can Help
Share this briefing with others
  Share with route planners, dispatchers, & management/staff
Provide feedback and suggestions
  Help identify issues/mitigations not yet identified
  Direct questions/comments to NEC ACR
Watch for additional information
  Flight Planners Telcon, NCF briefings, NBAA, CNS Taskforce, etc.
Plan resources for route planning & programming
  Updated Preferred IFR Routes were distributed on 9/22/2020
  Do not file the new Q-Routes before 11/5/2020
Be ready to utilize the new routes
  File the new Q-Routes beginning on 11/5/2020

## Slide 9: 9/10/2020 Q119 Publish Q119 SCOOB, VA TO WESTMINSTER, MD (EMI) VORTAC
ZDC
ZNY
Implement on 11/5/2020
SAMPLE DETAILED SLIDE
ADDITIONAL SLIDES AT THE END OF THIS PRESENTATION

## Slide 10: ZJX Q-Route/Y-Route NOTAMs
Q-Routes: Existing “ATC ASSIGNED ONLY” NOTAMs for the following Florida Q-Routes will be cancelled and reissued on 9/10/2020 and will be effective through 12/2/2021:
  Q85, Q87, Q97, Q109, Q113, Q135, Q409
Y-Routes: Existing “ATC ASSIGNED ONLY” NOTAMs for the following Florida Y-Routes will be cancelled and reissued on 9/10/2020 and will be effective through 12/2/2021:
  Y289, Y291, Y299, Y309, Y319, Y323
  The NA NOTAM for Y307 has been cancelled

## Slide 11: ZJX Q-Route NA NOTAMs Effective through 12/2/2021
FDC 0/9552 ZJX SC..NC..ROUTE ZJX. Q85 IGARY, SC TO SMPRR, NC. ATC ASSIGNED ONLY. 2009101058-2112020900
FDC 0/9554 ZJX SC..ROUTE ZJX. Q87 JROSS, SC TO LCAPE, SC. ATC ASSIGNED ONLY. 2009101059-2112020900
FDC 0/9563 ZJX SC..NC..ROUTE ZJX. Q97 CAKET, SC TO ELLDE, NC. ATC ASSIGNED ONLY. 2009101102-2112020900
FDC 0/9565 ZJX SC..ROUTE ZJX. Q109 PANDY, SC TO LAANA, NC. ATC ASSIGNED ONLY. 2009101103-2112020900
FDC 0/9567 ZJX SC..ROUTE ZJX. Q113 RAYVO, SC TO SARKY, SC. ATC ASSIGNED ONLY. 2009101105-2112020900
FDC 0/9569 ZJX SC..NC..ROUTE ZJX. Q135 JROSS, SC TO RAPZZ, NC. ATC ASSIGNED ONLY. 2009101107-2112020900
FDC 0/9577 ZJX SC..ROUTE ZJX. Q409 JROSS, SC TO MRPIT, NC.. ATC ASSIGNED ONLY. 2009101109-2112020900

## Slide 12: ZJX Y-Route NA NOTAMs Effective through 12/2/2021
FDC 0/9510 ZJX SC..GA..FL..ROUTE ZJX. Y289 DULEE, OA TO ZILLS, OA. ATC ASSIGNED ONLY. 2009101040-2112020900
FDC 0/9517 ZJX SC..GA..FL..ROUTE ZJX. Y291 HOAGG, OA TO SAGGY ,OA. ATC ASSIGNED ONLY. 2009101043-2112020900
FDC 0/9519 ZJX SC..GA..FL..ROUTE ZJX. Y299 GRUBR, OA TO JRDAN, OA. ATC ASSIGNED ONLY. 2009101044-2112020900
FDC 0/9521 ZJX SC..GA..FL..ROUTE ZJX. Y307 CARPX, OA TO GARIC, OA. ATC ASSIGNED ONLY. 2009101046-2112020900
FDC 0/9524 ZJX SC..GA..FL..ROUTE ZJX. Y309 PELCN, OA TO IDOLS, OA. ATC ASSIGNED ONLY. 2009101048-2112020900
FDC 0/9526 ZJX SC..GA..FL..ROUTE ZJX. Y319 OHLAA, OA TO IDOLS, OA. ATC ASSIGNED ONLY. 2009101049-2112020900
FDC 0/9528 ZJX SC..GA..FL..ROUTE ZJX. Y323 CARPX, OA TO IDOLS, OA. ATC ASSIGNED ONLY. 2009101050-2112020900

## Slide 13: NEC ACR Go Team
Utilize the Virtual Go-Team 11/5/2020-11/7/2020
  Open conference bridge staffed by subject matter experts available to address any ATC or operator issues
    888-924-3230 (direct 609-916-1975); Passcode: 817568
  Dates/Hours/Status Reports
    Thursday 11/5, 0600-1600, Status Reports @ 0600, 1000, 1400
    Friday 11/6, 0700-1600, Status Reports @ 0700, 1000, 1400
    Saturday 11/7, 0700-1200, Status Reports @ 0700, 1000
The NEC ACR Q-Route/Y-Route NA NOTAMs will be cancelled on 11/5/2020 at 0900 GMT
  Please do not file the new Q-Routes until 11/5/2020
THE ZJX Q-Route/Y-Route NOTAMs on the previous two slides will NOT be cancelled until 12/2/2021.

## Slide 14: NEC ACR ROUTE INFO
If you have specific questions for FAA Enroute Centers (ARTCCs), please feel free to contact the following directly:
ARTCC | Name | Phone | Email
Boston Center | Terry Drew | (603) 879-6808 | terrence.drew@faa.gov
Center | Dennis Tennett | (603) 879-6668 | dtennett@natca.net
New York Center | Bob Ocon | (631) 468-1015 | robert.ocon@faa.gov
Center | John Higgins | (631) 468-1373 | john.higgins@faa.gov
Washington Center | Cassie Blair | (407) 739-8075 | cassie.iddings@gmail.com
Center | Ben Dengler | (703) 771-3443 | benjamin.j.dengler@faa.gov
Atlanta Center | Danny McMillan | (770) 210-7703 | daniel.b.mcmillan@faa.gov
Center | Kevin Condon | (770) 210-7960 | kevin.w.condon@faa.gov
Jacksonville Center | Andrew Day | (904) 477-7305 | zjxoapm@gmail.com
Center | Ross Gibson | (904) 845-1768 | ross.gibson@faa.gov
Miami Center | Dave Petersen | (305) 716-1782 | dpetersen13@hotmail.com
Center | Andre Ferguson | (305) 716-1783 | andre.a.ferguson@faa.gov

## Slide 15: NEC ACR Changes - 2021
2/25/2021 (20) SIDs/STARs
  Amend RDU SIDs: (HOOKZ4, HURIC4, LWOOD4, OXFRD4, ROZBO4, BEXGO4, SHPRD4)
  Amend RDU STARs: (ALDAN3 RNAV, BLOGS3 RNAV, MALNR5 RNAV, BUZZY9 [conv])
  Delete RDU STARs (KAROO2 RNAV, ARGAL6 [conv], SOUTH BOSTON6[conv])
  Publish RDU TAQLE1 STAR
  Delete RDU SIDs (TAR HEEL1, FAYETTVILLE4, BLUE DEVIL6)
  Amend RDU SIDs: (RDU RALEIGH1, PACKK9)
10/7/2021 (28) Q-Route/Y-Route Additions/Amendments
  Publish New Q101, Q107, Q111, Q115(removed from list), Q117, Q131, Q133, Q167, Q419, Q445, Q481
  Publish New Q437(changed from original)
  Amend Q22, Q34(added to project), Q54, Q60, Q64, Q85, Q87, Q97, Q99, Q109, Q113, Q135, Q409
  Amend Y291, Y309, Y319, Y323
10/7/2021 (1) SID
  Amend ATL PHIIL3 SID
12/2/2021 (24) J-Route Deletions/Amendments
  Delete J55 (del TUBAS-PQI), J79, J121 (del CHS-BRIGS), J150, J165, J174, J191, J193, J207, J209, J222, J225, J506, J561, J563, J573, J582, J585
  Amend J14, J24, J37 (del LYH-ALB), J42, J52, J68
12/2/2021 (5) STARs
  Amend STARs: PHL (JIIMS4, PAATS4), EWR (PHLBO4), TEB (JAIKE4)
  Publish LGA PROUD1 STAR
All 2021 Dates Subject to Change Due to COVID-19

## Slide 16: ZDC High Altitude Sector Changes
Stratify Sectors 09 & 50 to create new Sector 30
Resulting 3 Sectors
  09 DIW Ultra High
    FL360-390
  50 YKT Ultra High
    FL360-390
  30 MSN Super High
    FL400-ABV
To help reduce sector workload/complexity and improve sector throughput
TENTATIVE 4/22/2021
50
09

## Slide 17: FAA Points of Contact
Paul Withers, FAA Management Co-Lead
paul.m.withers@faa.gov
904-710-5939
Joey Tinsley, NATCA Co-Lead
joseph.b.tinsley@faa.gov
770-363-1718

## Slide 18: Q-Routes – Detailed Slides
9/10/2020 (8) Q-Route Additions/Amendments
  Publish New Q119, Q127, Q129, Q220, Q430, Q439, Q450 per original 18-AEA-16
  Amend Q480 per original 18-AEA-16
NOTAM NA (Not Authorized for one chart cycle)
Implement on 11/5/2020

## Slide 19: 9/10/2020 Q119 Publish Q119 SCOOB, VA TO WESTMINSTER, MD (EMI) VORTAC
ZDC
ZNY
Implement on 11/5/2020

## Slide 20: 9/10/2020 Q127 Publish Q127 GORDONSVILLE, VA (GVE) VORTAC TO SMYRNA, DE (ENO) VORTAC
ZDC
Implement on 11/5/2020

## Slide 21: 9/10/2020 Q129 Publish Q129 GARIC, NC TO PYTON, MD
ZDC
ZOB
ZJX
Implement on 11/5/2020

## Slide 22: 9/10/2020 Q220 Publish Q220 RIFLE, NY TO LARIE, MA
ZBW
Implement on 11/5/2020

## Slide 23: 9/10/2020 Q430 Publish Q430 ZANDR, OH TO NANTUCKET, MA (ACK) VOR/DME
ZOB
ZNY
ZBW
Implement on 11/5/2020

## Slide 24: 9/10/2020 Q439 Publish Q439 BRIGS, NJ TO PRESQUE ISLE, ME (PQI) VOR/DME
ZDC
ZBW
Implement on 11/5/2020

## Slide 25: 9/10/2020 Q450 Publish Q450 HNNAH, NJ TO DEER PARK, NY (DPK) VOR/DME
ZNY
ZBW
Implement on 11/5/2020

## Slide 26: 9/10/2020 Q480 Amend Q480 Add KYLOH & BEEKN
ZBW
Implement on 11/5/2020

## Slide 27: J-Routes – Detailed Slides
11/5/2020 (11) J-Route/Q-Route Deletions/Amendments
  Delete J62, J109, J230, J570, Q108 per original 19-ASO-27
  Amend J2 (del TAY-DEFUN), J39 (del CEW-MGM), J61 (del EDDYS-EMI) per original 19-ASO-27
  Amend (with changes) J37 (del ALB-MSS), J55 (del CHS-TUBAS), J121 (del BRIGS-ENE)
    The above (J37/J55/J121) is a change to 19-ASO-27 and the procedure work currently in progress at AIS/AJV-A

## Slide 28: 11/5/2020 J2 Cancel Segment J2 DEFUN, FL to Taylor (TAY), FL
ZJX
Red Segment Being Deleted
Click to Return to Index

## Slide 29: 11/5/2020 J37 Cancel Segment J37 Albany (ALB), NY; to Massena (MSS), NY
ZNY
Red Segment Being Deleted
ZDC
ZBW
Click to Return to Index
Delete ALB-MSS only 11/5/2020
Additional changes on 12/2/2021

## Slide 30: 11/5/2020 J39 Cancel Segment J39 Crestview (CEW), FL to Montgomery (MGM), AL
ZJX
Red Segment Being Deleted
ZTL
Click to Return to Index

## Slide 31: 11/5/2020 J55 Cancel Segment J55 Charleston (CHS), SC to TUBAS, NC
J-Route Deleted in its Entirety
ZBW
ZJX
ZDC
Click to Return to Index
Delete CHS-TUBAS only 11/5/2020
Additional changes on 12/2/2021

## Slide 32: 11/5/2020 J61 Cancel Segment J61 EDDYS, NC to Westminster (EMI), MD
ZDC
Red Segment Being Deleted
ZNY
Click to Return to Index

## Slide 33: 11/5/2020 J62 Completely Deleted J62 Robbinsville (RBV), NJ; to Nantucket (ACK), MA
J-Route Deleted in its Entirety
ZBW
ZNY
Click to Return to Index

## Slide 34: 11/5/2020 J109 Completely Deleted J109 Wilmington (ILM), NC to Linden (LDN), VA
J-Route Deleted in its Entirety
ZDC
Click to Return to Index

## Slide 35: 11/5/2020 J121 Cancel Segment J121 BRIGS, NJ to Kennebunk (ENE), ME
J-Route Deleted in its Entirety
ZDC
ZBW
ZJX
Click to Return to Index
Delete BRIGS-ENE only 11/5/2020
Additional changes on 12/2/2021

## Slide 36: 11/5/2020 J230 Completely Deleted J230 Robbinsville (RBV), NJ to Bellaire (AIR), OH
J-Route Deleted in its Entirety
ZNY
ZOB
Click to Return to Index

## Slide 37: 11/5/2020 J570 Completely Deleted J570 Albany (ALB), NY to Mirabel (YMX), PQ, Canada
J-Route Deleted in its Entirety
ZBW
NavCanada
Segment(s) in Canada not depicted
Click to Return to Index

## Slide 38: 11/5/2020 Q108 Completely Deleted Q108 GADAY, AL to HKUNA, FL
J-Route Deleted in its Entirety
ZJX
Click to Return to Index